## Master Crosswalk & Analysis
The Cove / Cove Waterfront District - LEED-ND Rating System crosswalked to our analysis
Study area: Cove Waterfront District (official boundary from supplied KMZ, ~1,040 acres / 1.63 sq mi). Each row = one official LEED-ND line item; use the AutoFilter to sort by Tier / Status / Category / Timeline.
Category | Type | LEED-ND Item (official) | Max | Now | Poten- tial | Status | Feasibility tier | Timeline | Lead / Owner | Cost | Action / how to integrate
SLL | Prereq | Smart Location | Req |  |  | Met | 1 In hand | Year 1 | City Planning | $ | Infill location qualifies; document adjacency/connectivity.
SLL | Prereq | Imperiled Species & Ecological Communities | Req |  |  | Met (verify) | 1 In hand | Year 1 | Planning + FWC/USFWS | $ | Confirm no listed-species habitat; document.
SLL | Prereq | Wetland & Water Body Conservation | Req |  |  | At risk | 3 Capital/analysis | Year 2 | Environmental Svcs | $$ | Living shorelines / canal buffers; document seawall condition.
SLL | Prereq | Agricultural Land Conservation | Req |  |  | Met (N/A) | N/A | — | — | — | No farmland - no action.
SLL | Prereq | Floodplain Avoidance | Req |  |  | At risk | 3 Capital/analysis | Ongoing | Engineering + City | $$ | Qualify via previously-developed path; freeboard + resilient standards (Zone AE); build on FEMA CRS.
SLL | Credit | Preferred Locations | 10 | 5 | 7 | Partial | 3 Capital/analysis | Year 2 | Planning + consultant | $$ | Commission connectivity/adjacency analysis to claim it.
SLL | Credit | Brownfield Remediation | 2 | 0 | 0 | N/A | N/A | — | — | — | No known brownfield.
SLL | Credit | Access to Quality Transit | 7 | 1 | 3 | Partial | 3 Capital/analysis | Year 3 | BCT + City | $$$ | Advocate higher BCT frequency; upgrade shelters; document service.
SLL | Credit | Bicycle Facilities | 2 | 0 | 2 | Partial | 2 City program | Year 2 | City + Broward MPO | $$ | Bike lanes/racks linking Cove node, beach, A1A; join county network.
SLL | Credit | Housing & Jobs Proximity | 3 | 1 | 2 | Partial | 3 Capital/analysis | Year 2 | Planning | $ | Document jobs within 1/2 mile (retail + Hillsboro corridor).
SLL | Credit | Steep Slope Protection | 1 | 0 | 0 | N/A | N/A | — | — | — | Flat coastal site - not achievable.
SLL | Credit | Site Design for Habitat/Water Body | 1 | 0 | 0 | Not met | 4 Redevelopment | Ongoing | Environmental Svcs | $$ | Native shoreline planting/habitat features to pursue.
SLL | Credit | Restoration of Habitat/Wetlands | 1 | 0 | 0 | Not met | 4 Redevelopment | Ongoing | Environmental Svcs | $$ | Restore mangrove/native edge (e.g., near Sullivan Park).
SLL | Credit | Long-Term Conservation Management | 1 | 0 | 0 | Not met | 4 Redevelopment | Ongoing | Environmental Svcs | $ | Management plan for any restored habitat.
NPD | Prereq | Walkable Streets | Req |  |  | Partial | 3 Capital/analysis | Year 2 | Engineering | $$ | Sidewalk audit; fill gaps; entries face the street on corridors.
NPD | Prereq | Compact Development | Req |  |  | At risk | 4 Redevelopment | Ongoing | Planning/CRA/Commission | policy | Raise allowed net density on US-1 & Hillsboro edges.
NPD | Prereq | Connected & Open Community | Req |  |  | At risk | 3 Capital/analysis | Year 3 | Engineering | $$ | Ped cut-throughs; keep streets public & through-connected.
NPD | Credit | Walkable Streets | 9 | 3 | 4 | Partial | 3 Capital/analysis | Year 3 | Public Works | $$$ | Sidewalks, crossings, calming, street trees on grid + corridors.
NPD | Credit | Compact Development | 6 | 0 | 0 | Needs redevelopment | 4 Redevelopment | Ongoing | Planning/CRA | policy | Up to 6 with edge rezoning / multifamily infill.
NPD | Credit | Mixed-Use Neighborhoods | 4 | 1 | 2 | Partial | 3 Capital/analysis | Year 2 | Planning/CRA | $$ | Ground-floor retail + housing at node; more with corridor rezoning.
NPD | Credit | Housing Types & Affordability | 7 | 0 | 0 | Needs redevelopment | 4 Redevelopment | Ongoing | Planning/CRA/Commission | policy | Up to 7 with diverse + income-restricted corridor housing.
NPD | Credit | Reduced Parking Footprint | 1 | 0 | 0 | Needs redevelopment | 4 Redevelopment | Ongoing | CRA | policy | Shared/structured parking at the shopping center.
NPD | Credit | Connected & Open Community | 2 | 0 | 1 | Partial | 3 Capital/analysis | Year 3 | Engineering | $$ | Ped/bike connections; public through-streets.
NPD | Credit | Transit Facilities | 1 | 1 | 1 | Met | 1 In hand | Year 1 | City + BCT | $ | Maintain shelters/benches; add real-time info.
NPD | Credit | Transportation Demand Management | 2 | 0 | 0 | Needs redevelopment | 4 Redevelopment | Ongoing | City | policy | TDM program tied to redevelopment.
NPD | Credit | Access to Civic & Public Space | 1 | 1 | 1 | Met | 1 In hand | Year 1 | Planning/Parks | $ | Document Sullivan Park promenade / public waterfront.
NPD | Credit | Access to Recreation Facilities | 1 | 1 | 1 | Met | 1 In hand | Year 1 | Parks | $ | Document parks, pier, beach, Deerfield Island access.
NPD | Credit | Visitability & Universal Design | 1 | 0 | 0 | Not met | 4 Redevelopment | Ongoing | Building Dept. | policy | Adopt visitability standards for new/renovated homes.
NPD | Credit | Community Outreach & Involvement | 2 | 1 | 2 | Partial | 1 In hand | Year 1 | Cove Civic Assoc. + Planning | $ | Formalize charrette/engagement process.
NPD | Credit | Local Food Production | 1 | 1 | 1 | Met | 1 In hand | Year 1 | Cove Civic Assoc. | $ | Sustain the farmers market; add community garden.
NPD | Credit | Tree-Lined & Shaded Streetscapes | 2 | 1 | 2 | Partial | 2 City program | Year 2 | Environmental Svcs | $$ | Deploy Shady Street Tree program + giveaways; canopy inventory.
NPD | Credit | Neighborhood Schools | 1 | 1 | 1 | Met | 1 In hand | Year 1 | Planning | $ | Document walk access to St. Ambrose / Deerfield schools.
GIB | Prereq | Certified Green Building | Req |  |  | Not met | 4 Redevelopment | Ongoing | Commission/Building | policy | Require >=1 green-certified building on new construction/major reno.
GIB | Prereq | Minimum Building Energy Performance | Req |  |  | Not met | 4 Redevelopment | Ongoing | Building Dept. | policy | Energy-code compliance + retrofit incentives; document.
GIB | Prereq | Indoor Water Use Reduction | Req |  |  | Unknown | 4 Redevelopment | Ongoing | Building Dept. | policy | Low-flow fixture standards; document.
GIB | Prereq | Construction Activity Pollution Prevention | Req |  |  | N/A now | 4 Redevelopment | Ongoing | Engineering | policy | SWPPP/erosion control on future projects.
GIB | Credit | Certified Green Buildings | 5 | 0 | 0 | Needs redevelopment | 4 Redevelopment | Ongoing | Commission/Building | policy | Incentivize/require green certification for redevelopment.
GIB | Credit | Optimize Building Energy Performance | 2 | 0 | 0 | Needs redevelopment | 4 Redevelopment | Ongoing | Building Dept. | policy | Efficiency retrofits; high-performance envelope.
GIB | Credit | Indoor Water Use Reduction | 1 | 0 | 0 | Needs redevelopment | 4 Redevelopment | Ongoing | Building Dept. | policy | Low-flow retrofit program.
GIB | Credit | Outdoor Water Use Reduction | 2 | 0 | 2 | Partial | 2 City program | Year 2 | Cove Civic Assoc. + UF/IFAS | $ | Enroll in Broward NatureScape / Florida-Friendly Landscaping.
GIB | Credit | Building Reuse | 1 | 1 | 1 | Met | 1 In hand | Year 1 | Planning/Building | $ | Reuse-over-teardown preference.
GIB | Credit | Historic Resource Preservation / Adaptive Reuse | 2 | 0 | 1 | Partial | 3 Capital/analysis | Year 3 | Planning + Historical Society | $$ | Leverage Butler House; consider local designation.
GIB | Credit | Minimized Site Disturbance | 1 | 0 | 0 | N/A | N/A | — | — | — | Built-out; applies to infill only.
GIB | Credit | Rainwater Management | 4 | 0 | 1 | Partial | 3 Capital/analysis | Year 3 | Engineering/Stormwater | $$$ | Green stormwater at retail lot & ROW; leverage FEMA CRS.
GIB | Credit | Heat Island Reduction | 1 | 0 | 1 | Partial | 2 City program | Year 2 | Environmental Svcs | $$ | Shade trees + cool/permeable surfaces at the lot.
GIB | Credit | Solar Orientation | 1 | 0 | 0 | N/A | N/A | — | — | — | Applies to new layout only.
GIB | Credit | Renewable Energy Production | 3 | 0 | 0 | Needs redevelopment | 4 Redevelopment | Ongoing | Building/residents | $$$ | Rooftop/community solar program.
GIB | Credit | District Heating and Cooling | 2 | 0 | 0 | N/A | N/A | — | — | — | Not viable at this scale.
GIB | Credit | Infrastructure Energy Efficiency | 1 | 0 | 0 | Partial | 3 Capital/analysis | Ongoing | Public Works | $$ | LED streetlights; efficient stormwater pumps.
GIB | Credit | Wastewater Management | 2 | 0 | 0 | Weak | 4 Redevelopment | Ongoing | Utilities | $$$ | Greywater/reuse; nutrient reduction to protect ICW.
GIB | Credit | Recycled and Reused Infrastructure | 1 | 0 | 0 | Not met | 3 Capital/analysis | Ongoing | Public Works | $$ | Reuse road base/materials in ROW projects.
GIB | Credit | Solid Waste Management | 1 | 1 | 1 | Met | 1 In hand | Year 1 | City | $ | Maintain recycling; add construction-waste diversion.
GIB | Credit | Light Pollution Reduction | 1 | 0 | 1 | Partial | 1 In hand | Year 1 | Public Works/Code | $$ | Extend sea-turtle/dark-sky lighting standard inland.
ID | Credit | Innovation | 5 | 0 | 0 | Needs redevelopment | 4 Redevelopment | Ongoing | Project team | policy | Pilot exemplary strategies (resilience / living shoreline).
ID | Credit | LEED Accredited Professional | 1 | 0 | 0 | Needs redevelopment | 4 Redevelopment | Ongoing | Project team | $$ | Engage a LEED AP on any redevelopment.
RP | Credit | Regional Priority (x4, Region Defined) | 4 | 0 | 1 | Partial | 3 Capital/analysis | Ongoing | Planning | — | Pursue FL RP credits (rainwater/heat/water) once underlying earned.
SUMMARY
|  | Category | Max | Now | Achiev.
|  | Smart Location & Linkage | 28 | 7 | 14
|  | Neighborhood Pattern & Design | 41 | 11 | 16
|  | Green Infrastructure & Buildings | 31 | 2 | 8
|  | Innovation & Design Process | 6 | 0 | 0
|  | Regional Priority | 4 | 0 | 1
|  | TOTAL | 110 | 20 | 39
Now (as-is): ~20 pts ¦ Achievable without rezoning (Tiers 1-3): ~39 pts ¦ Max: 110 ¦ Certified 40-49 / Silver 50-59 / Gold 60-79 / Platinum 80+.
The ~39-pt 'Achievable' column is the improvement ceiling with NO rezoning/new buildings; the Action Plan tab sequences ~33 of it across Year 1-3.
Tier 4 (red) = only reachable through redevelopment / rezoning the US-1 & Hillsboro edges + a green-building requirement - the path from ~39 toward Certified.
LEED-ND rates NEW development; this is an interpretive read of an existing district for planning use. Boundary = official Cove Waterfront District study area (KMZ).

## Action Plan (Yr 1-3)
The Cove - LEED-ND Integration Action Plan (Year 1-3) with Credits Earned
Action | LEED-ND credit(s) earned | Pts | Lead / Owner | Cost | Neighborhood benefit
Phased plan to graft LEED-ND value into The Cove as-is. Cost key: $ = staff time/<$5k ¦ $$ = cost-share/study/$5-50k ¦ $$$ = capital $50k+ ¦ policy = process, not $$.
YEAR 1 - DOCUMENT & QUICK WINS (mostly free; claim what's already true)
Compile a neighborhood 'asset dossier' (parks, pier, farmers market, schools, bus stops, recycling) | Civic Space; Recreation; Local Food; Schools; Transit Facilities; Solid Waste | 6 | City Planning + Cove Civic Assoc. | $ | Claims 6 credits already true; produces a grant-ready asset map.
Adopt a 'reuse-over-teardown' preference for existing homes | Building Reuse | 1 | Planning / Building Dept. | $ | Preserves neighborhood character & embodied carbon.
Formalize a resident engagement process (regular charrettes) with the Cove Civic Assoc. | Community Outreach & Involvement | 2 | Cove Civic Assoc. + Planning | $ | Residents get a standing seat at planning.
Extend the sea-turtle / dark-sky lighting standard inland; begin fixture swaps | Light Pollution Reduction | 1 | Public Works / Code Enforcement | $$ | Safer, wildlife-friendly nights (city ordinance already exists).
Kick off street-tree planting via Deerfield's Shady Street Tree program + Arbor Day giveaways | (starts Tree-Lined & Heat Island - credited Yr 2) | 0 | Environmental Services + residents | $$ | Shade & cooling underway at cost-share pricing.
Enroll the neighborhood in Broward NatureScape / Florida-Friendly Landscaping | (starts Outdoor Water - credited Yr 2) | 0 | Cove Civic Assoc. + UF/IFAS Broward | $ | Water savings & cleaner canal runoff begin.
Year 1 subtotal | credits earned this year | 10
YEAR 2 - PROGRAMS MATURE + FIRST ANALYSES (low-moderate cost)
Reach street-tree canopy / shading targets (continue the program) | Tree-Lined & Shaded Streetscapes; Heat Island Reduction | 3 | Environmental Services | $$ | Cooler, shadier, more walkable streets.
Achieve NatureScape Silver/Gold recognition (native + smart irrigation) | Outdoor Water Use Reduction | 2 | Cove Civic Assoc. + UF/IFAS | $ | Lower water bills; less fertilizer into the ICW.
Install bike racks + first bike-lane/greenway links (Cove node -> beach & park) | Bicycle Facilities | 2 | City + Broward MPO | $$ | Safe biking to shops, park, beach.
Commission a connectivity/adjacency + jobs-proximity study | Preferred Locations; Housing & Jobs Proximity | 7 | Planning + consultant | $$ | Formalizes the 'smart location' story; grant-ready.
Begin BCT service advocacy + shelter design | (starts Access to Transit - credited Yr 3) | 0 | City + Broward County Transit | $ | Builds the pipeline to better bus service.
Sidewalk-gap audit + priority crossing design | (starts Walkable Streets - credited Yr 3) | 0 | Engineering / Public Works | $$ | A prioritized walk-safety plan.
Year 2 subtotal | credits earned this year | 14
YEAR 3 - CAPITAL PROJECTS & GREEN INFRASTRUCTURE (budget required; still NO rezoning)
Build sidewalk / crossing / traffic-calming improvements | Walkable Streets | 4 | Public Works / Engineering | $$$ | Safer everyday walking on the grid & corridors.
Green stormwater retrofit at the shopping-center lot & ROW (bioswales, permeable paving) | Rainwater Management | 1 | Engineering / Stormwater | $$$ | Less flooding, cleaner canal/ICW water; logs for FEMA CRS.
Deliver higher BCT frequency + upgraded shelters | Access to Quality Transit | 3 | Broward County Transit + City | $$$ | A real car-optional mobility option.
Pursue Butler House / a local historic designation | Historic Resource Preservation | 1 | Planning + Deerfield Historical Society | $$ | Protects heritage; opens preservation grants.
Year 3 subtotal | credits earned this year | 9
ONGOING / FUTURE - TIER 4 POLICY TRACK (not counted below - this is the path PAST ~33 toward Certified)
US-1 & Hillsboro EDGE rezoning / mixed-use + higher-density study | Compact Development; Housing Types & Affordability; Mixed-Use | ~17 | Planning + CRA + City Commission | policy/$$ | Biggest point block AND biggest change - a deliberate policy decision.
Green-building requirement + retrofit incentives for new construction | Certified Green Buildings; Energy; Renewables | ~12 | City Commission / Building Dept. | policy | Unlocks the GIB prerequisites needed for actual certification.
TOTAL INTEGRATED WITH NO REZONING / NO NEW BUILDINGS: ~33 LEED-ND points over 3 years
CUMULATIVE (no rezoning, no new buildings): end of Yr 1 ~10 pts -> end of Yr 2 ~24 -> end of Yr 3 ~33 pts of LEED-ND value integrated.
Every action is a real improvement (shade, water, stormwater, walk/bike, wildlife lighting, public waterfront) - the credits are the scorecard, not the goal.
To cross from ~33 into Certified (40-49) / Silver: pursue the Tier-4 policy track (edge rezoning + green-building requirement) as a separate Commission/CRA decision.
Points are interpretive estimates; confirm specifics with Deerfield Beach Planning & Zoning / GIS and Environmental Services before adopting.

## Integrate Now - Qualify For
The Cove - Integrating LEED-ND As-Is: What We Can Qualify For (no certification required)
LEED-ND Credit | Pts | How to integrate into The Cove (as-is) | Why it improves the neighborhood
The question: not 'how do we get certified' but 'which LEED-ND ideas can we graft onto The Cove as-is to improve it - and what do we qualify for?'
TIER 1 - ALREADY QUALIFY / JUST DOCUMENT IT (essentially in hand today)
Access to Civic & Public Space | 1 | Document Sullivan Park promenade + public waterfront access. | Protects & showcases public waterfront - the neighborhood's signature asset.
Access to Recreation Facilities | 1 | Document walk/bike access to Sullivan Park, the pier, the beach, Deerfield Island shuttle. | Confirms The Cove as a recreation-rich district.
Local Food Production | 1 | Recognize the Cove / Butler House farmers market; add a community-garden plot. | Local food + a recurring community gathering.
Neighborhood Schools | 1 | Document walkable access to St. Ambrose + Deerfield schools. | Supports walk-to-school & family retention.
Transit Facilities | 1 | Inventory BCT stops/shelters on US-1 & Hillsboro; add benches/real-time signs. | Makes the bus a real option at the edges.
Building Reuse | 1 | Adopt a 'reuse-over-teardown' preference for existing homes. | Keeps neighborhood character & embodied carbon.
Solid Waste Management | 1 | Document the city curbside recycling program; add construction-waste diversion. | Cleaner waste stream, little cost.
Light Pollution Reduction | 1 | Deerfield ALREADY enforces a sea-turtle/coastal lighting ordinance (Broward Beach Lighting Mgmt Plan) - extend fixture standards inland. | Dark-sky, wildlife-friendly, safer streets.
Community Outreach & Involvement | 2 | Formalize a charrette/engagement process with the active Cove Civic Association. | Gives residents a real seat at planning.
Subtotal - Tier 1 (in hand / document) | 10
TIER 2 - PLUG INTO A PROGRAM THE CITY/COUNTY ALREADY RUNS (low cost, high benefit)
Tree-Lined & Shaded Streetscapes | 2 | Deploy Deerfield's 'Shady Street Tree' cost-share + free tree giveaways + $50-100 rebates, street by street. | Shade, cooler walks, curb appeal, stormwater help.
Outdoor Water Use Reduction | 2 | Enroll The Cove in Broward NatureScape / Florida-Friendly Landscaping (Silver/Gold); native + smart irrigation. | Lower water bills; less fertilizer/runoff into the canals.
Heat Island Reduction | 1 | Pair the tree canopy with light/permeable surfaces at the shopping-center lot & rights-of-way. | Cooler, more comfortable public realm.
Bicycle Facilities | 2 | Add bike racks at the Cove node + connect to the county bike/greenway network toward the beach. | Safer biking to shops, park, beach.
Subtotal - Tier 2 (existing programs) | 7
TIER 3 - A CAPITAL / STREETSCAPE PROJECT OR ANALYSIS (budget yes, rezoning NO)
Preferred Locations | 7 | Already a qualifying infill location - commission the connectivity/adjacency analysis to claim it. | Formalizes The Cove's 'smart location' story for grants.
Walkable Streets | 4 | Sidewalk gap-fill, marked crossings, traffic calming, street trees on the grid + corridors. | Safer, more walkable everyday streets.
Access to Quality Transit | 3 | Advocate higher BCT frequency on US-1/Hillsboro; upgrade shelters; document service. | Better mobility without a car.
Housing & Jobs Proximity | 2 | Document jobs within 1/2 mile (Cove retail + Hillsboro corridor). | Confirms a real live-work balance.
Rainwater Management | 1 | Green stormwater (bioswales, permeable paving) at the retail lot & ROW; build on the city's FEMA-CRS floodplain program. | Less flooding + cleaner canal/ICW water.
Historic Resource Preservation | 1 | Leverage the Butler House / consider a local historic designation. | Protects heritage; opens preservation grants.
Subtotal - Tier 3 (capital / analysis) | 18
TIER 4 - ONLY WITH REDEVELOPMENT / NEW BUILDINGS (not now - this is where certification really lives)
Compact Development / Housing Types / Mixed-Use | 17 | Would require rezoning the US-1 & Hillsboro EDGES for mixed-use + higher density. | Biggest point block AND biggest change - a separate policy decision.
Certified Green Buildings / Energy / Renewables | 12 | Would require a green-building requirement + retrofits on new construction. | Unlocks the GIB prerequisites over time.
Reduced Parking / TDM | 3+ | Tied to redevelopment of the shopping-center site. | Only makes sense with a redevelopment project.
Subtotal - Tier 4 (needs redevelopment - informational) | 29
ACHIEVABLE WITH NO REZONING / NO NEW BUILDINGS (Tiers 1-3): ~30 points ¦ Tier 1 (~10) is essentially in hand now
BOTTOM LINE: with NO rezoning and NO new buildings, The Cove can realistically integrate/qualify for ~30 points of LEED-ND strategies -
Tier 1 (~10) is essentially in hand today; Tiers 2-3 add ~20 more through existing city/county programs and streetscape projects.
Every one of these is a genuine neighborhood improvement (shade, water, stormwater, walk/bike, wildlife lighting, public waterfront) - the points are a bonus, not the goal.
The jump PAST ~30 toward Certified (40) is Tier 4 - a deliberate redevelopment/rezoning choice for the US-1 & Hillsboro edges, not an as-is improvement.
Local programs referenced: Deerfield Beach Tree Programs (Shady Street Tree, giveaways, rebates); Broward NatureScape / Florida-Friendly Landscaping; Deerfield sea-turtle lighting ordinance; FEMA Community Rating System (city participant).

## The Cove - Scored + Actions
The Cove, Deerfield Beach FL - LEED-ND Scored As-Is + Actions to Improve
Type | Credit / Prerequisite | Max | Now | Potential | Status | What to do to bring it up to speed
SMART LOCATION & LINKAGE (max 28)
Prereq | Smart Location | Req |  |  | Met | Infill site already qualifies. Maintain; document adjacency/connectivity.
Prereq | Imperiled Species & Ecological Communities | Req |  |  | Met (verify) | Pull FWC/USFWS records to confirm no listed-species habitat; keep documentation.
Prereq | Wetland & Water Body Conservation | Req |  |  | At risk | Built to seawalls, no buffers. Add living shorelines / vegetated canal buffers where feasible; document existing condition.
Prereq | Agricultural Land Conservation | Req |  |  | N/A | No farmland - no action.
Prereq | Floodplain Avoidance | Req |  |  | At risk | Largely FEMA Zone AE. Qualify via the previously-developed/infill path; adopt freeboard + flood-resilient construction standards.
Credit | Preferred Locations | 10 | 5 | 7 | Partial | Document intersection density & adjacency; add east-side street/ped connections to raise the score.
Credit | Brownfield Remediation | 2 | 0 | 0 | N/A | No known brownfield; only pursue if a contaminated parcel is identified & cleaned.
Credit | Access to Quality Transit | 7 | 1 | 3 | Partial | Partner with Broward County Transit for higher bus frequency on US-1/Hillsboro; add sheltered stops; document service levels.
Credit | Bicycle Facilities | 2 | 0 | 1 | Partial | Add bike lanes + racks linking the Cove node, beach and A1A; connect to the county bike network.
Credit | Housing and Jobs Proximity | 3 | 1 | 2 | Partial | Document jobs within 1/2 mile (Cove retail + Hillsboro corridor); add jobs through mixed-use edge redevelopment.
Credit | Steep Slope Protection | 1 | 0 | 0 | N/A | Flat coastal site - not achievable.
Credit | Site Design for Habitat/Water Body | 1 | 0 | 0 | Not met | Add native shoreline planting / habitat features along canals & the ICW to pursue.
Credit | Restoration of Habitat/Wetlands | 1 | 0 | 0 | Not met | Restore a mangrove/native edge segment (e.g., near Sullivan Park) to earn.
Credit | Long-Term Conservation Management | 1 | 0 | 0 | Not met | Adopt a written long-term management plan for any restored habitat.
| Subtotal - Smart Location & Linkage | 28 | 7 | 13
NEIGHBORHOOD PATTERN & DESIGN (max 41)
Prereq | Walkable Streets | Req |  |  | Partial | Sidewalk-gap audit; fill missing segments; require building entries to face the street on corridors.
Prereq | Compact Development | Req |  |  | At risk | Single-family density is below the minimum. Raise allowed net density on US-1 & Hillsboro edges to satisfy the prereq.
Prereq | Connected & Open Community | Req |  |  | At risk | Improve intersection density; add pedestrian cut-throughs between finger-canal streets; keep streets public.
Credit | Walkable Streets | 9 | 3 | 5 | Partial | Continuous sidewalks, street trees, on-street parking, and facade/entry standards along US-1 & Hillsboro.
Credit | Compact Development | 6 | 0 | 1 | Weak | Allow mixed-use / multifamily infill on the two arterial edges to lift net residential density.
Credit | Mixed-Use Neighborhoods | 4 | 1 | 2 | Partial | Encourage ground-floor retail + housing at the Cove node and along US-1; broaden the use mix within walking distance.
Credit | Housing Types and Affordability | 7 | 0 | 1 | Weak | Add housing types (townhome/duplex/ADU/apartment) and income-restricted units on corridor infill.
Credit | Reduced Parking Footprint | 1 | 0 | 0 | Not met | Shared/structured parking + reduced minimums at the shopping center; convert some surface lot.
Credit | Connected and Open Community | 2 | 0 | 1 | Partial | Add ped/bike connections; ensure new streets are public and through-connected.
Credit | Transit Facilities | 1 | 1 | 1 | Met | Maintain shelters/benches at stops; add real-time arrival info.
Credit | Transportation Demand Management | 2 | 0 | 0 | Not met | Launch a TDM program (transit passes, bike share, carpool) anchored at the retail node.
Credit | Access to Civic & Public Space | 1 | 1 | 1 | Met | Maintain Sullivan Park promenade and public waterfront access.
Credit | Access to Recreation Facilities | 1 | 1 | 1 | Met | Maintain access to parks, pier, beach and Deerfield Island Park.
Credit | Visitability and Universal Design | 1 | 0 | 0 | Not met | Adopt visitability standards (zero-step entry, wider doors) for new/renovated homes.
Credit | Community Outreach and Involvement | 2 | 1 | 2 | Partial | Formalize a charrette/engagement process with the Cove Civic Association and document it.
Credit | Local Food Production | 1 | 1 | 1 | Met | Sustain the farmers market; add community-garden space.
Credit | Tree-Lined and Shaded Streetscapes | 2 | 1 | 2 | Partial | Canopy inventory + street-tree planting program to meet the shading thresholds.
Credit | Neighborhood Schools | 1 | 1 | 1 | Met | Maintain walkable access to St. Ambrose / Deerfield schools; add safe-routes-to-school.
| Subtotal - Neighborhood Pattern & Design | 41 | 11 | 19
GREEN INFRASTRUCTURE & BUILDINGS (max 31)
Prereq | Certified Green Building | Req |  |  | Not met | DECISIVE GAP. Require >=1 green-certified building (LEED/FGBC) in any new construction or major renovation.
Prereq | Minimum Building Energy Performance | Req |  |  | Not met | Existing 1956 stock. Require energy-code compliance + retrofit incentives; document on new/renovated buildings.
Prereq | Indoor Water Use Reduction | Req |  |  | Unknown | Adopt low-flow fixture standards for renovations/new build; document.
Prereq | Construction Activity Pollution Prevention | Req |  |  | N/A now | Applies to active construction. Require SWPPP/erosion control on future projects.
Credit | Certified Green Buildings | 5 | 0 | 0 | Not met | Incentivize/require green certification for redevelopment (target the shopping-center & corridor projects).
Credit | Optimize Building Energy Performance | 2 | 0 | 0 | Not met | Efficiency retrofits; solar-ready + high-performance envelope standards.
Credit | Indoor Water Use Reduction | 1 | 0 | 0 | Not met | Low-flow fixture retrofit program.
Credit | Outdoor Water Use Reduction | 2 | 0 | 0 | Weak | Florida-Friendly landscaping, smart irrigation, native/xeric plantings.
Credit | Building Reuse | 1 | 1 | 1 | Met | Continue adaptive reuse over teardown where practical.
Credit | Historic Resource Preservation / Adaptive Reuse | 2 | 0 | 1 | Partial | Leverage Butler House / any historic structures; consider local historic designation.
Credit | Minimized Site Disturbance | 1 | 0 | 0 | N/A | Built-out. Applies to infill - protect soils & trees on new construction.
Credit | Rainwater Management | 4 | 0 | 1 | Partial | Green stormwater infrastructure (bioswales, permeable paving) at the retail lot & ROW; cut canal nutrient loading.
Credit | Heat Island Reduction | 1 | 0 | 0 | Weak | Cool/permeable pavement, shade trees, reflective roofs at the shopping center.
Credit | Solar Orientation | 1 | 0 | 0 | N/A | Applies to new layout; adopt solar-ready orientation for infill.
Credit | Renewable Energy Production | 3 | 0 | 0 | Not met | Rooftop / community-solar program; solar on the shopping-center roof.
Credit | District Heating and Cooling | 2 | 0 | 0 | Not met | Not viable at this scale - skip.
Credit | Infrastructure Energy Efficiency | 1 | 0 | 0 | Not met | LED streetlights; efficient pumps on canal/stormwater infrastructure.
Credit | Wastewater Management | 2 | 0 | 0 | Weak | Explore greywater/reuse; nutrient reduction to protect the Intracoastal.
Credit | Recycled and Reused Infrastructure | 1 | 0 | 0 | Not met | Reuse road base/materials in future right-of-way projects.
Credit | Solid Waste Management | 1 | 1 | 1 | Met | Maintain curbside recycling; add construction-waste diversion.
Credit | Light Pollution Reduction | 1 | 0 | 1 | Partial | Dark-sky-compliant fixtures (important near the ICW / wildlife).
| Subtotal - Green Infrastructure & Buildings | 31 | 2 | 5
INNOVATION & DESIGN PROCESS (max 6)
Credit | Innovation | 5 | 0 | 0 | Not met | Pilot exemplary strategies (resilience / living shoreline / stormwater) for innovation points.
Credit | LEED Accredited Professional | 1 | 0 | 0 | Not met | Put a LEED AP on any redevelopment team.
| Subtotal - Innovation & Design Process | 6 | 0 | 0
REGIONAL PRIORITY (max 4)
Credit | Regional Priority (x4, Region Defined) | 4 | 0 | 1 | Partial | Pursue Florida-relevant RP credits (rainwater / heat island / water) once the underlying credits are achieved.
| Subtotal - Regional Priority | 4 | 0 | 1
| PROJECT TOTAL (interpretive) | 110 | 20 | 38 | < Certified | Certified 40-49 ¦ Silver 50-59 ¦ Gold 60-79 ¦ Platinum 80+
HOW IT SCORES NOW: ~20 points as-is -> BELOW the 40-pt Certified floor.
CEILING FROM THE ACTIONS LISTED ABOVE (conservative): ~38 points - still just short of Certified.
PATH TO CERTIFIED (40-49) / SILVER: the big swings are STRUCTURAL - rezone the US-1 & Hillsboro EDGES for
mixed-use/higher density (Compact Development, Housing Types, Mixed-Use) and REQUIRE green building on new
construction (unlocks the GIB prerequisites + Certified Green Buildings + Energy). Those moves add ~15-25 pts over time.
REMINDER: LEED-ND certifies NEW development projects; this is an interpretive read of an existing neighborhood for planning use.

## Neighborhood Development Plan
|  |  | LEED v4 for Neighborhood Development Plan |  |  |  | Project Name:
|  |  | Project Checklist |  |  |  | Date:
Yes | ? | No |  |  |  | Yes | ? | No
|  |  | Smart Location & Linkage | [5 empty] | Green Infrastructure & Buildings
Y |  |  | Prereq | Smart Location | Required | Y |  |  | Prereq | Certified Green Building | Required
Y |  |  | Prereq | Imperiled Species and Ecological Communities | Required | Y |  |  | Prereq | Minimum Building Energy Performance | Required
Y |  |  | Prereq | Wetland and Water Body Conservation | Required | Y |  |  | Prereq | Indoor Water Use Reduction | Required
Y |  |  | Prereq | Agricultural Land Conservation | Required | Y |  |  | Prereq | Construction Activity Pollution Prevention | Required
Y |  |  | Prereq | Floodplain Avoidance | Required |  |  |  | Credit | Certified Green Buildings | 5
|  |  | Credit | Preferred Locations | 10 |  |  |  | Credit | Optimize Building Energy Performance | 2
|  |  | Credit | Brownfield Remediation | 2 |  |  |  | Credit | Indoor Water Use Reduction | 1
|  |  | Credit | Access to Quality Transit | 7 |  |  |  | Credit | Outdoor Water Use Reduction | 2
|  |  | Credit | Bicycle Facilities | 2 |  |  |  | Credit | Building Reuse | 1
|  |  | Credit | Housing and Jobs Proximity | 3 |  |  |  | Credit | Historic Resource Preservation and Adaptive Reuse | 2
|  |  | Credit | Steep Slope Protection | 1 |  |  |  | Credit | Minimized Site Disturbance | 1
|  |  | Credit | Site Design for Habitat or Wetland and Water Body Conservation | 1 |  |  |  | Credit | Rainwater Management | 4
|  |  | Credit | Restoration of Habitat or Wetlands and Water Bodies | 1 |  |  |  | Credit | Heat Island Reduction | 1
|  |  | Credit | Long-Term Conservation Management of Habitat or Wetlands and Water Bodies | 1 |  |  |  | Credit | Solar Orientation | 1
[9 empty] | Credit | Renewable Energy Production | 3
|  |  | Neighborhood Pattern & Design | [5 empty] | Credit | District Heating and Cooling | 2
Y |  |  | Prereq | Walkable Streets | Required |  |  |  | Credit | Infrastructure Energy Efficiency | 1
Y |  |  | Prereq | Compact Development | Required |  |  |  | Credit | Wastewater Management | 2
Y |  |  | Prereq | Connected and Open Community | Required |  |  |  | Credit | Recycled and Reused Infrastructure | 1
|  |  | Credit | Walkable Streets | 9 |  |  |  | Credit | Solid Waste Management | 1
|  |  | Credit | Compact Development | 6 |  |  |  | Credit | Light Pollution Reduction | 1
|  |  | Credit | Mixed-Use Neighborhoods | 4
|  |  | Credit | Housing Types and Affordability | 7 |  |  |  | Innovation & Design Process
|  |  | Credit | Reduced Parking Footprint | 1 |  |  |  | Credit | Innovation | 5
|  |  | Credit | Connected and Open Community | 2 |  |  |  | Credit | LEED® Accredited Professional | 1
|  |  | Credit | Transit Facilities | 1
|  |  | Credit | Transportation Demand Management | 2 |  |  |  | Regional Priority Credits
|  |  | Credit | Access to Civic & Public Space | 1 |  |  |  | Credit | Regional Priority Credit: Region Defined | 1
|  |  | Credit | Access to Recreation Facilities | 1 |  |  |  | Credit | Regional Priority Credit: Region Defined | 1
|  |  | Credit | Visitability and Universal Design | 1 |  |  |  | Credit | Regional Priority Credit: Region Defined | 1
|  |  | Credit | Community Outreach and Involvement | 2 |  |  |  | Credit | Regional Priority Credit: Region Defined | 1
|  |  | Credit | Local Food Production | 1
|  |  | Credit | Tree-Lined and Shaded Streetscapes | 2 |  |  |  | PROJECT TOTALS (Certification estimates)
|  |  | Credit | Neighborhood Schools | 1 | Certified: 40-49 points, Silver: 50-59 points, Gold: 60-79 points, Platinum: 80+ points

## Neighborhood Development
|  |  | LEED v4 for Neighborhood Development Built Project |  |  |  | Project Name: | The Cove, Deerfield Beach FL - INTERPRETIVE (see notes)
|  |  | Project Checklist |  |  |  | Date: | 2026-07-03
Yes | ? | No
|  |  | Smart Location & Linkage | [5 empty] | Green Infrastructure & Buildings
Y |  |  | Prereq | Smart Location | Required |  |  | N | Prereq | Certified Green Building | Required
Y |  |  | Prereq | Imperiled Species and Ecological Communities | Required |  |  | N | Prereq | Minimum Building Energy Performance | Required
| ? |  | Prereq | WetlandS and Water Body Conservation | Required |  | ? |  | Prereq | Indoor Water Use Reduction | Required
Y |  |  | Prereq | Agricultural Land Conservation | Required | Y |  |  | Prereq | Construction Activity Pollution Prevention | Required
| ? |  | Prereq | Floodplain Avoidance | Required |  |  |  | Credit | Certified Green Buildings | 5
5 | 2 |  | Credit | Preferred Locations | 10 |  |  |  | Credit | Optimize Building Energy Performance | 2
|  |  | Credit | Brownfield Remediation | 2 |  |  |  | Credit | Indoor Water Use Reduction | 1
1 | 2 |  | Credit | Access to Quality Transit | 7 |  |  |  | Credit | Outdoor Water Use Reduction | 2
| 1 |  | Credit | Bicycle Facilities | 2 | 1 |  |  | Credit | Building Reuse | 1
1 | 1 |  | Credit | Housing and Jobs Proximity | 3 |  | 1 |  | Credit | Historic Resource Preservation and Adaptive Reuse | 2
|  |  | Credit | Steep Slope Protection | 1 |  |  |  | Credit | Minimized Site Disturbance | 1
|  |  | Credit | Site Design for Habitat or Wetland and Water Body Conservation | 1 |  | 1 |  | Credit | Rainwater Management | 4
|  |  | Credit | Restoration of Habitat or Wetlands and Water Bodies | 1 |  |  |  | Credit | Heat Island Reduction | 1
|  |  | Credit | Long-Term Conservation Management of Habitat or Wetlands and Water Bodies | 1 |  |  |  | Credit | Solar Orientation | 1
[9 empty] | Credit | Renewable Energy Production | 3
|  |  | Neighborhood Pattern & Design | [5 empty] | Credit | District Heating and Cooling | 2
Y |  |  | Prereq | Walkable Streets | Required |  |  |  | Credit | Infrastructure Energy Efficiency | 1
| ? |  | Prereq | Compact Development | Required |  |  |  | Credit | Wastewater Management | 2
| ? |  | Prereq | Connected and Open Community | Required |  |  |  | Credit | Recycled and Reused Infrastructure | 1
3 | 2 |  | Credit | Walkable Streets | 9 | 1 |  |  | Credit | Solid Waste Management | 1
| 1 |  | Credit | Compact Development | 6 |  | 1 |  | Credit | Light Pollution Reduction | 1
1 | 1 |  | Credit | Mixed-Use Neighborhoods | 4
| 1 |  | Credit | Housing Types and Affordability | 7 |  |  |  | Innovation & Design Process
|  |  | Credit | Reduced Parking Footprint | 1 |  |  |  | Credit | Innovation | 5
| 1 |  | Credit | Connected and Open Community | 2 |  |  |  | Credit | LEED® Accredited Professional | 1
1 |  |  | Credit | Transit Facilities | 1
|  |  | Credit | Transportation Demand Management | 2 |  |  |  | Regional Priority Credits
1 |  |  | Credit | Access to Civic & Public Space | 1 |  |  |  | Credit | Regional Priority Credit: Region Defined | 1
1 |  |  | Credit | Access to Recreation Facilities | 1 |  | 1 |  | Credit | Regional Priority Credit: Region Defined | 1
|  |  | Credit | Visitability and Universal Design | 1 |  |  |  | Credit | Regional Priority Credit: Region Defined | 1
1 | 1 |  | Credit | Community Outreach and Involvement | 2 |  |  |  | Credit | Regional Priority Credit: Region Defined | 1
1 |  |  | Credit | Local Food Production | 1
1 | 1 |  | Credit | Tree-Lined and Shaded Streetscapes | 2 |  |  |  | Project Totals (Certification estimates)
1 |  |  | Credit | Neighborhood Schools | 1 | Certified: 40-49 points, Silver: 50-59 points, Gold: 60-79 points, Platinum: 80+ points
INTERPRETIVE LEED-ND EVALUATION - The Cove, Deerfield Beach FL (2026-07-03)
NOT an official certification. LEED-ND rates NEW development/redevelopment projects; The Cove is an existing 1956 neighborhood.
Point cells above = interpretive estimate of how the existing neighborhood aligns with each credit (col A/J = likely; col B/K = possible/partial).
PREREQUISITE REALITY (decisive): GIB 'Certified Green Building' and 'Minimum Building Energy Performance' are NOT met for existing housing;
'Wetland & Water Body Conservation', 'Floodplain Avoidance' (FEMA Zone AE), 'Compact Development' (low density) and 'Connected & Open Community' are AT RISK.
=> As-is, The Cove could NOT be certified without new green-building activity and prerequisite documentation.
INTERPRETIVE SCORE: ~20 'likely' points; up to ~41 if every partial/uncertain credit is pursued & documented. Realistic ~28-32 -> below the 40-pt Certified floor.
STRENGTHS: infill location, parks/recreation (Sullivan Park, pier, Deerfield Island), walkable retail node, schools, farmers market, tree canopy, civic association.
WEAKNESSES: low residential density, limited housing diversity/affordability, car-dependent transit, coastal floodplain exposure, no green-building/energy program.